## MOM Tracker
Sr. No. | Activity | Action Required | Team Responsible | Current Status | Priority | What is Completed | What is Still Left
1 | Company Dashboard | Create centralized company activity view | Development Team | Partial | High | Company pages/detail views exist with contacts/prospects/activity context, but the full war-room dashboard with every requested tab and unified company task view still needs final polish. | Complete/verify centralized company activity timeline, company tasks tab, demo records tab, and export/print-ready layout.
2 | Activity Tracker | Add company-wise task and follow-up tracker | Development Team | Partial | High | Activities and follow-up reminders exist; stale prospect reminder digest now batches prospects in one email. | Finish company-wise task/follow-up tracker view and make sure company dashboard shows all pending follow-ups in one place.
3 | Service & Product Separation | Create separate workflows and stages | Development Team | Done | High | Multiple pipelines/workflows exist, including Sales, Active, Partner/Enterprise-style pipeline handling, and Projects service type badges. | Keep pipeline naming/order aligned with operations as usage evolves.
4 | Project Stage Automation | Add drag-and-drop stage movement | Development Team | Partial / Revised | High | Projects and stage movement exist, but prospect drag-and-drop was intentionally removed per latest request and replaced with direct stage controls. | Confirm whether Projects board should keep drag-and-drop or also move fully to explicit stage-change controls.
5 | Project Tracking Fields | Add manpower, timeline, and delay tracking | Development Team | Done | High | Project fields, progress, delay flags/reasons, team members, and tasks exist in schema/services/UI. | Tighten permissions for who can add team members, e.g. project lead/admin only if required.
6 | Timeline Tracker | Create start date, end date, and progress tracking | Development Team | Partial | Medium | Start/end dates and progress are present on projects/prospects; stage-linked progress behavior has been requested and should be verified end-to-end. | Ensure progress auto-increments by stage and timeline/Gantt view is production-ready.
7 | Demo Tracking | Add demo and discovery call records | Development Team | Done | High | Demo records service/router/logger flow exists and links demos to contacts/prospects/companies with outcomes and next actions. | Validate UX from all entry points: contact, company, prospect, and activities.
8 | Lead Tracking | Add lead stages, reminders, and follow-up tracking | Development Team | Done | High | Lead/contact statuses, prospect pipeline stages, follow-up reminders, and activity logging are implemented. | Continue improving filters/reporting around first contact and lead source attribution.
9 | Communication Tracking | Add mail and discussion tracking | Development Team | Partial | Medium | Activity logging supports communication channels such as calls, emails, WhatsApp, notes, meetings, and tasks. | Full email thread/discussion sync is not confirmed; add mailbox integration if required.
10 | Client Information Section | Primary contact should be present in prospects to prevent back-and-forth from contacts and prospects | Development Team | Done | Medium | Primary contact details are shown directly on prospect detail and denormalized fields exist. | Make sure imports/backfills populate primary contact consistently for older records.
11 | Sales Pipeline Dashboard | Add opportunity and conversion dashboard | Development Team | Partial | High | Dashboard/reporting modules exist with prospect contribution, pipeline widgets, and sales reports. | Confirm management dashboard composition and public/shareable view expectations.
12 | SOC 2 Workflow | Create SOC 2 tracking workflow | Development Team | Partial | Medium | SOC 2 service badges/custom fields and project/prospect tracking support exist. | Finalize SOC 2-specific stages, checklist/tasks, and audit evidence workflow if needed.
13 | DPDP Workflow | Create DPDP tracking workflow | Development Team | Partial | Medium | DPDP custom/service classification support exists in project/prospect workflow. | Finalize DPDP-specific fields, checklist, and reporting workflow.
14 | Partner Lead Tracking | Add partner-referred lead tracking | Development Team | Done | Medium | Partner module supports partner-linked prospects and partner-sourced prospect creation/attachment. | Add richer partner conversion analytics if management wants revenue attribution dashboards.
15 | 3+ Day No-Activity Reminder Digest | Send one batched email per owner instead of separate emails per prospect | Development Team | Done | High | Reminder service groups inactive open prospects by owner and sends one table-based email. Lost prospects are excluded. CC added for runal@seccomply.net and shivani@seccomply.net. | Deploy latest code and verify SMTP/Resend accepts CC recipients.

## Summary
MOM CRM Updates Tracker
Generated On | 20 May 2026
Status | Count
Done | 7
Partial / Revised | 1
Partial | 7
Pending | 0
Notes
Statuses are based on current code inspection and the MOM screenshots shared in chat.
Internal table/router names may still say deal/deals; the UI has been renamed to prospect/prospects as requested.
The no-activity reminder digest is implemented as one table email per owner and excludes lost prospects.